## Summary_known_issue
S/N | core-v-verif ticket# | Known issue | Category | Status | Random/Custom | Example failing test(s) | Example error message(s)
1 |  | Simulation error due to ebreak and haltreq at same time and ISS model has different priority in serving compare to core. Status: Pending updates from Imperas ISS model to have same behaviour as core. | Imperas | Open (80% fixed) | Random | corev_rand_debug, corev_rand_interrupt_debug, corev_rand_pulp_hwloop_debug, corev_rand_pulp_instr_debug, corev_rand_interrupt_debug, corev_rand_debug_ebreak, corev_rand_pulp_hwloop_count_range_test | illegal DUT response to a set of asynchronous net changes mismatches on dcrs registers mismatches on these instr(s) -> bnez, cv.srl.sc.h, wfi, remu, lw
2 |  | Build error due to offset between hwloop0_end_stream1_id0 label and cv.endi instruction can not fit in 12 bits. Status: Pending fix but in lower priority because is seed related and very rare to occur. | verif | Open (80% fixed) | Random | corev_rand_pulp_hwloop_test
3 |  | Simulation error due to Interrupt routine handler is playing with mstatus.fs, leaving it at OFF state when exited. This corrupts the global setting made by TEST_CFG=floating_pt_instr_en. Status: Pending fix | verif | Open (80% fixed) | Random | corev_rand_interrupt_nested